## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
PB-01 | S1 | US-001 | Study workflows & define requirements | MUST HAVE | No dependency | Aditya & Sandhiya | Completed
PB-02 | S2 | US-001 | Design system architecture | MUST HAVE | Flask, SQLAlchemy, Postgres SQL, React, NLTK | Aditya & Sandhiya | Completed
PB-03 | S3 | US-001 | Design database schema | MUST HAVE | Postgres SQL, SQLAlchemy | Aditya | Completed
PB-04 | S4 | US-001 | Design data pipelines | MUST HAVE | Google Gemini, spaCy, NLTK | Upasona | Completed
PB-05 | S5 | US-001 | Feedback | MUST HAVE | Google genai | Upasona | Completed
PB-06 | S6 | US-001 | AI Prioritization & Business Impact Analysis | MUST HAVE | Google Gemini API | Sasi | Completed
PB-07 | S07 | US-001 | PRD & User story Generation | MUST HAVE | Flask, Flask-JWT-Extended, google-genai, python-dotenv, Flask-SQLAlchemy, SQLAlchemy, psycopg2-binary, uuid, logging | Sasi | Completed
PB-08 | S08 | US-001 | Conversational Product Intelligence Assistant (RAG) | MUST HAVE | Flask, Flask-JWT-Extended, google-genai, python-dotenv, Flask-SQLAlchemy, SQLAlchemy, psycopg2-binary, uuid, logging | Sasi & Sandhiya | Completed
PB-09 | S9 | US-001 | Roadmap Planning | MUST HAVE | Flask, Flask-JWT-Extended, google-genai | Yasaswine | Completed
PB-10 | S10 | US-001 | Reporting & Dashboard | MUST HAVE | Flask, Flask-JWT-Extended, google-genai, python-dotenv, Flask-SQLAlchemy, SQLAlchemy, psycopg2-binary, React, axios, react-router-dom, SVG, uuid, logging, datetime | Yasaswine | Completed
PB-11 | S11 | US-001 | Final integration and validation completed | MUST HAVE | No dependency | All Team Members | Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | TASK ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 109 | 34 | 33 | 19 | 9 | 5 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG | [22 empty] | Completed | 8
US-001 | 1 | Study workflows & define requirements | 2026-07-09 | 2026-07-11 | Aditya & Sandhiya | Others | Completed | 9 | Day 1: 3; Day 2: 3; Day 3: 3
US-001 | 2 | Design system architecture | 2026-07-11 | 2026-08-12 | Aditya & Sandhiya | Design | Completed | 8 | Day 1: 4; Day 2: 4
US-001 | 3 | Design database schema | 2026-07-13 | 2026-07-14 | Aditya | Design | Completed | 8 | Day 1: 4; Day 2: 4
US-001 | 4 | Design data pipelines | 2026-07-15 | 2026-08-16 | Upasona | Coding & Design | Completed | 9 | Day 1: 5; Day 2: 4
US-001 | 5 | Feedback | 2026-07-16 | 2026-08-18 | Upasona | Coding | Completed | 15 | Day 1: 5; Day 2: 6; Day 3: 4
US-001 | 6 | AI Prioritization & Business Impact Analysis | 2026-07-29 | 2026-07-31 | Sasi | Coding | Completed | 8 | Day 1: 3; Day 2: 3; Day 3: 2
US-001 | 7 | PRD & User story Generation | 2026-08-31 | 2026-08-03 | Sasi | Coding | Completed | 9 | Day 1: 2; Day 2: 2; Day 3: 2; Day 4: 3
US-001 | 8 | Conversational Product Intelligence Assistant (RAG) | 2026-08-03 | 2026-08-05 | Sasi & Sandhiya | Coding | Completed | 7 | Day 1: 2; Day 2: 2; Day 3: 3
US-001 | 9 | Roadmap Planning | 2026-08-10 | 2026-08-16 | Yasaswine | Coding | Completed | 8 | Day 1: 1; Day 2: 1; Day 3: 1; Day 4: 1; Day 5: 1; Day 6: 1; Day 7: 2
US-001 | 10 | Reporting & Dashboard | 2026-08-16 | 2026-08-23 | Yasaswine | Coding | Completed | 11 | Day 1: 1; Day 2: 1; Day 3: 1; Day 4: 2; Day 5: 2; Day 6: 1; Day 7: 1; Day 8: 2
US-001 | 11 | Final integration and validation completed | 2026-08-23 | 2026-08-28 | All Team Members | Debugging | Completed | 17 | Day 1: 4; Day 2: 3; Day 3: 3; Day 4: 3; Day 5: 2; Day 6: 2
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | What Was Completed | What Will Be Done Next | Impediments | Action Taken | Owner
S1 | Day 2 | Requirements and workflow reviewed | Finalize project goals and user stories | Initial requirement ambiguity | Team discussion with mentor and documented decisions | Aditya & Sandhiya
S2 | Day 4 | Project goal and workflow documented | Review architecture direction | Unclear technical boundaries | Conducted team brainstorming and architecture review | Aditya & Sandhiya
S3 | Day 6 | Database requirements identified | Finalize data model | Dependency between data and architecture | Aligned schema with system design | Aditya
S4 | Day 10 | Data pipeline design progressed | Complete processing flow | Data quality and transformation questions | Reviewed pipeline assumptions and test data | Upasona
S5 | Day 14 | AI prioritization logic implemented | Tune prioritization outputs | Inconsistent AI recommendations | Compared outputs with business rules and refined prompts | Upasona
S6 | Day 18 | PRD/user-story generation completed | Integrate generated outputs | Need for consistent story structure | Added validation criteria and output checks | Sasi
S7 | Day 22 | RAG assistant connected to knowledge layer | Improve retrieval and responses | Retrieval relevance issues | Adjusted retrieval context and tested sample queries | Sasi & Sandhiya
S8 | Day 26 | Conversational product intelligence integrated | Validate end-to-end flow | Integration edge cases | Performed joint testing across modules | Sasi & Sandhiya
S9 | Day 30 | Roadmap planning flow completed | Connect roadmap to dashboard | Prioritization-to-roadmap mapping | Reviewed mapping rules with team | Yasaswine
S10 | Day 34 | Dashboard/reporting features completed | Final validation and polish | Minor UI/data consistency issues | Cross-checked dashboard metrics and outputs | Yasaswine
S11 | Day 38 | Final integration and validation completed | Prepare final review | Last-minute integration checks | Completed regression testing and consolidated feedback | All Team Members

## Retrospection
Stop Doing | Continue Doing | Action Taken
Assuming requirements are complete | Participating actively in discussions | Held mentor/team review and documented project goals.
Delaying dependency identification | Keeping design aligned with requirements | Reviewed architecture and database dependencies before implementation.
Waiting until the end to validate pipeline output | Documenting data-processing decisions | Added early checks and reviewed sample outputs with the team.
Accepting first-pass AI recommendations | Iterating on prompts and prioritization logic | Refined AI rules and compared recommendations with expected priorities.
Creating stories without validation criteria | Collaborating on PRD and user-story quality | Added clearer acceptance criteria and reviewed generated stories.
Leaving retrieval testing until integration | Improving conversational response quality | Adjusted retrieval context and validated sample conversations.
Testing only after feature completion | Working closely with backend/data contributors | Resolved integration edge cases through joint testing.
Treating roadmap planning as a separate activity | Reviewing prioritization with the team | Aligned roadmap items with prioritized backlog outputs.
Waiting until final review for data checks | Keeping reporting simple and decision-focused | Cross-checked dashboard metrics and corrected inconsistencies.
Deferring integration fixes to the last moment | Communicating blockers and reviewing deliverables | Completed final validation and consolidated feedback for release readiness.