## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | sandhiya-sk | 2026-08-25 | NameError occurred for gemini_model_name inside ask_gemini_assistant. | S11 | sandhiya-sk | Logical | Resolved the gemini_model_name NameError inside ask_gemini_assistant. | 2026-08-25 | Closed | Source: commit 27de69e9
2 | sandhiya-sk | 2026-08-23 | NLTK find raised ValueError/OSError and the dotenv loading path was incorrect in the test runner. | S11 | sandhiya-sk | Logical | Corrected NLTK resource handling and dotenv loading path in the test runner. | 2026-08-23 | Closed | Source: commit f7d487b3
3 | sandhiya-sk | 2026-08-21 | Light-theme accessibility contrast issue in the markdown renderer, assistant chat feeds, and roadmap modal. | S11 | sandhiya-sk | User Interface | Resolved the light-theme accessibility contrast issues across the affected UI components. | 2026-08-21 | Closed | Source: commit ceb024ef
4 | sandhiya-sk | 2026-08-23 | Dotenv path/loading issue affected the apply recommendations endpoints. | S11 | sandhiya-sk | Maintainability | Fixed dotenv path loading and completed the apply recommendations endpoints. | 2026-08-23 | Closed | Source: commit 0b5846e2
5 | sandhiya-sk | 2026-08-25 | Chatbot fallback behavior required a retry loop when the primary model could not complete generation. | S08 | sandhiya-sk | Logical | Implemented a fallback model retry loop and added a sample 100-row test CSV. | 2026-08-25 | Closed | Source: commit 87034d17
6 | Kundam Sasi Rekha | 2026-08-08 | AI Classification module required a defect fix. | S09 | Kundam Sasi Rekha | Logical | Fixed Module 4 AI Classification. | 2026-08-08 | Closed | Source: commit abab74a1
7 | Kundam Sasi Rekha | 2026-08-10 | Merge/integration conflict occurred while combining feature modules 6, 7 and 8. | S09 | Kundam Sasi Rekha | Others | Resolved merge conflicts and integrated the module changes. | 2026-08-05 | Closed | Source: commits 108a3b5c / 04d6b4dd

## Sheet2
Logical
User Interface
Maintainability
Standards
Others